## NATPET
DAILY SHIPMENT STATUS REPORT 26/11/2017 - NETPET
S. no. | Our Job No | Customer Name | Order No. | Shipment Recived Date | B/L Number | Number Of Containers |  | Terminal | Shipping Line | Vessel Name | ETA |  | CC Days | Manifest documents Recived Date | Bayan NO. | Rotation NO. | Initial Bayan Date | Pre-Bayan | Manifest to Initial Bayan Printed | Initial Bayan to Pre Bayan Printed | Shuttling |  | Final Bayan Date | Shuttle to final bayan | Random Inspection | Custom Exam Of Containers no. | New Seal no. | Load Permit Printed On | Total Expenses |  |  |  | Status | Remarks | Reason for the delay (Shutout) (If any)
[6 empty] | 20 ft. | 40 ft. |  |  |  | On or About | Revised ETA Date | [8 empty] | Start Date | End Date | [6 empty] | Custom Duty | Inspection | Container Seal | Total
1 | NAT1 | NATPET | 8107611 | 24/8/2017 | MSCUL5488802 |  | 4 |  | MEDITERRANEAN SHIPPING COMPANY | MSC RITA | 27/8/2017 | 28/8/2017 | 3 | 24/8/2017 | 9224 |  | 24-8-2017 | 26-8-2017 | 0 | 2 | 26-08-2017 | 27/8/2017 | 28-08-2017 | 2 |  | Non | - | [5 empty] | Completed | Completed
207 | NAT207 | NATPET | 8108215 | 2017-11-16 | MSCUJ5525157 |  | 5 |  | MEDITERRANEAN SHIPPING COMPANY | MSC HEIDI | 2017-11-14 | 2017-11-22 | -2 | 2017-11-18 | 12835 | 836/31 | 2017-11-19 | 2017-11-20 | 1 | 1 | 2017-11-20 | 2017-11-21 | 2017-11-21 | 1 |  | NON | - | [5 empty] | Completed | Completed
208 | NAT208 | NATPET | 8108254 | 2017-11-18 | MSCUJ5525611 |  | 1 |  | MEDITERRANEAN SHIPPING COMPANY | MAERSK EUREKA | 2017-11-28 | 2017-11-29 | 10 | 2017-11-18 | 12959 | 853/7 | 2017-11-22 | 2017-11-25 | 4 | 3 | 2017-11-25 |  |  | -43064 |  | NON | - | [5 empty] | UNDER PROCESS | Waiting for container to reach at port
209 | NAT209 | NATPET | 8108259 | 2017-11-18 | MSCUJ5525652 |  | 1 |  | MEDITERRANEAN SHIPPING COMPANY | MAERSK EUREKA | 2017-11-28 | 2017-11-29 | 10 | 2017-11-18 | 12957 | 853/8 | 2017-11-22 | 2017-11-25 | 4 | 3 | 2017-11-25 |  |  | -43064 |  | NON | - | [5 empty] | UNDER PROCESS | Waiting for container to reach at port
210 | NAT210 | NATPET | 8108244 | 2017-11-18 | MSCUJ5525223 |  | 4 |  | MEDITERRANEAN SHIPPING COMPANY | MSC SAVERIA | 2017-11-29 | 2017-11-29 | 11 | 2017-11-18 | 12833 | 849/5 | 2017-11-19 | 2017-11-20 | 1 | 1 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2 |  | NON | - | [5 empty] | Completed | Completed
211 | NAT211 | NATPET | 8108245 | 2017-11-18 | MSCUJ5525140 |  | 5 |  | MEDITERRANEAN SHIPPING COMPANY | MSC SAVERIA | 2017-11-29 | 2017-11-29 | 11 | 2017-11-18 | 12832 | 849/3 | 2017-11-19 | 2017-11-20 | 1 | 1 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2 |  | NON | - | [5 empty] | Completed | Completed
212 | NAT212 | NATPET | 8108246 | 2017-11-18 | MSCUJ5525165 |  | 5 |  | MEDITERRANEAN SHIPPING COMPANY | MSC SAVERIA | 2017-11-29 | 2017-11-29 | 11 | 2017-11-18 | 12872 | 849/4 | 2017-11-20 | 2017-11-22 | 2 | 2 | 2017-11-22 | 2017-11-23 | 2017-11-23 | 1 |  | NON | - | [5 empty] | Completed | Completed
213 | NAT213 | NATPET | 8108247 | 2017-11-18 | MSCUJ5525132 |  | 4 |  | MEDITERRANEAN SHIPPING COMPANY | MSC SAVERIA | 2017-11-29 | 2017-11-29 | 11 | 2017-11-18 | 12834 | 849/2 | 2017-11-19 | 2017-11-20 | 1 | 1 | 2017-11-20 | 2017-11-21 | 2017-11-21 | 1 |  | NON | - | [5 empty] | Completed | Completed
214 | NAT214 | NATPET | 8108267 | 2017-11-18 | MSCUJ5527096 |  | 1 |  | MEDITERRANEAN SHIPPING COMPANY | CSAV TYNDALL | 2017-11-28 | 2017-11-29 | 10 | 2017-11-21 |  |  | 2017-11-22 |  | 1 | -43061 |  |  |  | 0 |  | NON | - | [5 empty] | UNDER PROCESS | B/L not updated in Saudi EDI
215 | NAT215 | NATPET | 8108266 | 2017-11-18 | MSCUJ5527104 |  | 1 |  | MEDITERRANEAN SHIPPING COMPANY | CSAV TYNDALL | 2017-11-28 | 2017-11-29 | 10 | 2017-11-21 |  |  |  |  | -43060 | 0 |  |  |  | 0 |  | NON | - | [5 empty] | UNDER PROCESS | B/L not updated in Saudi EDI
216 | NAT216 | NATPET | 8108262 | 2017-11-18 | MSCUJ5526163 |  | 8 |  | MEDITERRANEAN SHIPPING COMPANY | MSC MELISSA | 2017-11-26 | 2017-11-26 | 8 | 2017-11-20 | 12856 | 840/34 | 2017-11-20 | 2017-11-21 | 0 | 1 | 2017-11-21 | 2017-11-23 | 2017-11-23 | 2 |  | NON | - | [5 empty] | Completed | Completed
217 | NAT217 | NATPET | 8108257 | 2017-11-18 | MSCUJ5526155 |  | 2 |  | MEDITERRANEAN SHIPPING COMPANY | MAERSK EUREKA | 2017-11-28 | 2017-11-29 | 10 | 2017-11-20 | 12955 | 853/11 | 2017-11-22 | 2017-11-25 | 2 | 3 | 2017-11-25 |  |  | -43064 |  | NON | - | [5 empty] | UNDER PROCESS | Waiting for container to reach at port
218 | NAT218 | NATPET | 8108258 | 2017-11-18 | MSCUJ5526122 |  | 2 |  | MEDITERRANEAN SHIPPING COMPANY | MAERSK EUREKA | 2017-11-28 | 2017-11-29 | 10 | 2017-11-20 | 12954 | 853/10 | 2017-11-22 | 2017-11-25 | 2 | 3 | 2017-11-25 |  |  | -43064 |  | NON | - | [5 empty] | UNDER PROCESS | Waiting for container to reach at port
219 | NAT219 | NATPET | 8108255 | 2017-11-18 | MSCUJ5526098 |  | 2 |  | MEDITERRANEAN SHIPPING COMPANY | MAERSK EUREKA | 2017-11-28 | 2017-11-29 | 10 | 2017-11-20 | 12952 | 853/13 | 2017-11-22 | 2017-11-25 | 2 | 3 | 2017-11-25 |  |  | -43064 |  | NON | - | [5 empty] | UNDER PROCESS | Waiting for container to reach at port
225 | NAT225 | NATPET | 8108273 | 2017-11-20 | MSCUJ5526908 |  | 22 |  | MEDITERRANEAN SHIPPING COMPANY | MSC MELISSA | 2017-11-26 | 2017-11-26 | 6 | 2017-11-26 | 12912 | 840/56 | 2017-11-21 | 2017-11-23 | -5 | 2 | 2017-11-23 | 2017-11-25 | 2017-11-26 | 3 |  | NON | - | [5 empty] | Completed | Waiting for final bayan copy
227 | NAT227 | NATPET | 8108299 | 2017-11-22 | MSCUJ5526676 |  | 3 |  | MEDITERRANEAN SHIPPING COMPANY | MSC MELISSA | 2017-11-26 | 2017-11-26 | 4 | 2017-11-21 | 12945 | 840/43 | 2017-11-22 | 2017-11-23 | 1 | 1 | 2017-11-23 | 2017-11-25 |  | -43062 |  | NON | - | [5 empty] | UNDER PROCESS | Under taking department | Under taking department
228 | NAT228 | NATPET | 8108256 | 2017-11-22 | MSCUJ5527393 |  | 4 |  | MEDITERRANEAN SHIPPING COMPANY | MAERSK EUREKA | 2017-11-28 | 2017-11-27 | 6 | 2017-11-23 | 13068 | 862/3 | 2017-11-25 | 2017-11-26 | 2 | 1 | 2017-11-26 |  |  | -43065 |  | NON | - | [5 empty] | UNDER PROCESS | Waiting for container to reach at port
229 | NAT229 | NATPET | 8108268 | 2017-11-22 | MSCUJ5527468 |  | 1 |  | MEDITERRANEAN SHIPPING COMPANY | CSAV TYNDALL | 2017-11-28 | 2017-11-29 | 6 | 2017-11-23 |  |  |  |  | -43062 | 0 |  |  |  | 0 |  | NON | - | [5 empty] | UNDER PROCESS | B/L not updated in Saudi EDI
230 | NAT230 | NATPET | 8108270 | 2017-11-22 | MSCUJ5527617 |  | 22 |  | MEDITERRANEAN SHIPPING COMPANY | MSC MELISSA | 2017-11-26 | 2017-11-26 | 4 | 2017-11-23 | 12999 | 840/70 | 2017-11-23 | 2017-11-25 | 0 | 2 | 2017-11-25 |  |  | -43064 |  | NON | - | [5 empty] | UNDER PROCESS | Waiting for container to reach at port
231 | NAT231 | NATPET | 8108271 | 2017-11-22 | MSCUJ5527641 |  | 22 |  | MEDITERRANEAN SHIPPING COMPANY | MSC MELISSA | 2017-11-26 | 2017-11-26 | 4 | 2017-11-23 | 13042 | 840/86 | 2017-11-23 | 2017-11-25 | 0 | 2 | 2017-11-25 |  |  | -43064 |  | NON | - | [5 empty] | UNDER PROCESS | Waiting for container to reach at port
232 | NAT232 | NATPET | 8108172 | 2017-11-23 | MSCUJ5527484 |  | 22 |  | MEDITERRANEAN SHIPPING COMPANY | MSC MELISSA | 2017-11-26 | 2017-11-26 | 3 | 2017-11-22 | 12998 | 840/69 | 2017-11-23 | 2017-11-25 | 1 | 2 | 2017-11-25 |  |  | -43064 |  | NON | - | [5 empty] | UNDER PROCESS | Waiting for container to reach at port
233 | NAT233 | NATPET | 8108274 | 2017-11-26 |  |  | 2 |  | MEDITERRANEAN SHIPPING COMPANY | MSC MARIA SAVERIA | 2017-11-29 |  | 3 | [5 empty] | 0 | 0 |  |  |  | 0 |  | NON | - | [5 empty] | UNDER PROCESS | No manifest
234 | NAT234 | NATPET | 8108315 | 2017-11-23 | MSCUJ5527567 |  | 2 |  | MEDITERRANEAN SHIPPING COMPANY | CSAV TYNDALL | 2017-11-28 | 2017-11-29 | 5 | 2017-11-23 |  |  |  |  | -43062 | 0 |  |  |  | 0 |  | NON | - | [5 empty] | UNDER PROCESS | B/L not updated in Saudi EDI
235 | NAT235 | NATPET | 8108265 | 2017-11-25 | MSCUJ5528201 |  | 4 |  | MEDITERRANEAN SHIPPING COMPANY | MAERSK EUREKA | 2017-11-28 | 2017-11-29 | 3 | 2017-11-25 | 13110 | 853/26 | 2017-11-26 |  | 1 | -43065 |  |  |  | 0 |  | NON | - | [5 empty] | UNDER PROCESS | Waiting for pre bayan to print at port

## No. of Days
MANIFESST - Intial Bayan |  |  | Intial Bayan - Pre Bayan |  |  | Shuttling - Final Bayan
Max | 4 |  | Max | 3 |  | Max | 3
Min | -43062 |  | Min | -43065 |  | Min | -43065
Avg | -5381.7917 |  | Avg | -3587.1667 |  | Avg | -17942.7083
Same Day | 5 | 25% | Same Day | 4 | 18.18% | Same Day | 6 | 42.86%
After 1 Day | 8 | 40% | After 1 Day | 7 | 31.82% | After 1 Day | 3 | 21.43%
After 2 Days | 5 | 25% | After 2 Days | 6 | 27.27% | After 2 Days | 4 | 28.57%
After 5 Days | 2 | 10% | After 5 Days | 5 | 22.73% | After 5 Days | 1 | 7.143%
| 20 |  |  | 22 |  |  | 14